## Instructions
DenOS launch test plan
Run sandbox tests first. Do not switch to live Stripe until all launch gates pass.
Workbook use | Enter tester, date, evidence, actual result, and status for every row.
Status | Use Not Started, In Progress, Pass, Fail, Blocked, or Not Applicable.
Sandbox | Use Stripe test keys and test cards. Keep the API and Stripe CLI listener running.
Live Stripe | Use live keys only after deployment, HTTPS, backups, policies, and webhook verification are complete.
Test data | Never reuse sandbox family or athlete records in production.
Go-live gate | Every Critical test must be Pass. High tests must be Pass or have a documented owner and resolution date.
Refund limitation | For older installment orders with multiple collected invoices, verify each paid invoice in Stripe before declaring a full historical refund complete.
Security | Never paste secret keys, webhook secrets, passwords, or full card data into this workbook.
Sources | https://docs.stripe.com/testing ¦ https://docs.stripe.com/webhooks ¦ https://docs.stripe.com/refunds ¦ https://docs.stripe.com/payments/checkout/customization

## Sandbox tests
Sandbox tests
Use Stripe sandbox/test mode only. Record evidence such as order ID, screenshot name, or Stripe event ID.
ID | Area | Scenario / action | Expected result | Priority | Tester | Test date | Evidence / reference | Actual result | Status
S-01 | Startup | Start PostgreSQL, API, frontend, and Stripe CLI listener. | Health endpoint reports connected; login and portal load. | Critical |  |  |  |  | Not Started
S-02 | Staff auth | Log in with valid staff credentials. | Admin dashboard loads; customer-only portal data is not exposed. | Critical |  |  |  |  | Not Started
S-03 | Staff auth | Attempt staff login with wrong password. | Login is rejected without revealing whether the email exists. | High |  |  |  |  | Not Started
S-04 | Parent registration | Register a new family with valid guardian, athlete, USA Wrestling number, password, and all required waivers. | Family, guardian, athlete, account, pending USA submission, and 365-day waiver signatures are created. | Critical |  |  |  |  | Not Started
S-05 | Registration validation | Try an invalid email, short password, missing athlete, missing USA number, and unsigned required waiver. | Each submission is blocked with a useful message. | High |  |  |  |  | Not Started
S-06 | Authorization | Log in as Parent A and attempt to access Parent B data/API identifiers. | Request is forbidden or not found; no other-family data appears. | Critical |  |  |  |  | Not Started
S-07 | Parent account | Change parent email using current password, sign out, then sign in using new email. | Guardian and login emails match; old email no longer logs in. | High |  |  |  |  | Not Started
S-08 | Family archive | Archive a family while parent is logged in. | Tokens are revoked, login is disabled, and history remains. Restore re-enables access. | Critical |  |  |  |  | Not Started
S-09 | Athletes | Parent adds a second athlete with required fields and USA Wrestling number. | Athlete belongs only to that family and USA status is Pending. | Critical |  |  |  |  | Not Started
S-10 | Waivers | Sign every active required waiver for each athlete. | Signature shows guardian, athlete, version, timestamp, hash, and expiration 365 days later. | Critical |  |  |  |  | Not Started
S-11 | USA Wrestling | Verify a submitted card as Current. | It disappears from review queue and expires on next August 31. | High |  |  |  |  | Not Started
S-12 | Products | Create limited-session and unlimited products with validity periods. | Products appear in parent catalog with correct price and terms. | Critical |  |  |  |  | Not Started
S-13 | Discounts | Create manual percentage and fixed discounts; test valid, invalid, expired, and product-restricted codes. | Only eligible codes apply; order snapshot retains the code and amount. | High |  |  |  |  | Not Started
S-14 | Sibling discount | Buy for first distinct athlete, then second through fourth. | First is full price; configured automatic sibling discounts apply to eligible positions without typed code. | Critical |  |  |  |  | Not Started
S-15 | Discount management | Deactivate and reactivate a discount. | Inactive discount cannot apply; historical orders remain unchanged. | Medium |  |  |  |  | Not Started
S-16 | One-time checkout | Buy a package with Stripe test card 4242 4242 4242 4242. | Checkout shows DenOS, order completes, package activates once, and webhook returns HTTP 200. | Critical |  |  |  |  | Not Started
S-17 | Declined checkout | Use Stripe test card 4000 0000 0000 0002. | Payment is declined; no active package is granted. | Critical |  |  |  |  | Not Started
S-18 | Idempotency | Resend the same successful checkout webhook. | No duplicate package or duplicate discount redemption is created. | Critical |  |  |  |  | Not Started
S-19 | Reconciliation | Stop listener, complete a test checkout, restart API, and use Check Stripe status. | Paid order becomes Completed and package activates securely. | High |  |  |  |  | Not Started
S-20 | Installments | Buy an equal monthly payment product. | Subscription is created; access activates while payment is current; amount and installment count are correct. | Critical |  |  |  |  | Not Started
S-21 | Fixed billing day | Buy a plan with a fixed day of month. | Subscription schedules correctly; access is active before first scheduled installment when subscription is valid. | High |  |  |  |  | Not Started
S-22 | Failed installment | Generate a failure tied to the real test subscription. | IsPaymentCurrent becomes false and check-in blocks with payment-plan overdue. | Critical |  |  |  |  | Not Started
S-23 | Recovered installment | Pay the failed test invoice. | IsPaymentCurrent returns true and check-in eligibility is restored. | Critical |  |  |  |  | Not Started
S-24 | Check-in | Check in an eligible limited-package athlete twice. | Each check-in creates attendance history and reduces sessions by exactly one. | Critical |  |  |  |  | Not Started
S-25 | Unlimited check-in | Check in an eligible unlimited-package athlete. | Attendance is logged without decrementing a numeric balance. | High |  |  |  |  | Not Started
S-26 | Eligibility | Try check-in with missing waiver, non-current USA card, expired package, zero sessions, and overdue payment. | Each condition blocks check-in with the correct reason. | Critical |  |  |  |  | Not Started
S-27 | Override | Perform staff eligibility override with and without a reason. | Reason is required; successful override is visibly and permanently audited. | High |  |  |  |  | Not Started
S-28 | Attendance | Review recent attendance and family Attendance tab. | Athlete, family, package, timestamp, staff, notes, and override status are correct. | High |  |  |  |  | Not Started
S-29 | Refund | Refund a completed one-time order from DenOS with a reason. | Stripe refund succeeds; order shows Refunded / canceled; package deactivates; audit entry remains. | Critical |  |  |  |  | Not Started
S-30 | Subscription refund | Refund/cancel an installment order from DenOS. | Collected Checkout payment is refunded, future subscription charges stop, and access is removed. | Critical |  |  |  |  | Not Started
S-31 | Stripe-side refund | Refund a matched payment directly in Stripe. | Signed refund webhook marks order Refunded and deactivates package. | High |  |  |  |  | Not Started
S-32 | Persistence | Restart API and frontend after purchases, check-ins, and refunds. | All states and audit history persist correctly. | Critical |  |  |  |  | Not Started
S-33 | Concurrency | Double-click purchase/check-in/refund actions and refresh during processing. | No duplicate grants, deductions, refunds, or inconsistent states occur. | High |  |  |  |  | Not Started
S-34 | Responsive UI | Complete parent registration and purchase on phone-sized display. | All required controls and messages remain usable. | Medium |  |  |  |  | Not Started
S-35 | Secrets | Inspect Git status/history and browser network responses. | No Stripe secret, webhook secret, DB password, or parent password is committed or returned. | Critical |  |  |  |  | Not Started

## Live Stripe tests
Live Stripe tests
Run only after the production environment, legal pages, backups, and live webhook are ready.
ID | Area | Scenario / action | Expected result | Priority | Tester | Test date | Evidence / reference | Actual result | Status
L-01 | Environment | Confirm production URL uses HTTPS and sandbox database is not connected. | Production health is good and production data store is isolated. | Critical |  |  |  |  | Not Started
L-02 | Secrets | Configure live sk_live key and live endpoint whsec in hosting secret manager. | Secrets are not in source, logs, browser, or workbook. | Critical |  |  |  |  | Not Started
L-03 | Webhook | Create public live webhook with all required events and send Stripe test event. | Endpoint returns HTTP 200 and signature verification succeeds. | Critical |  |  |  |  | Not Started
L-04 | Branding | Set Stripe business/display name to DenOS and upload logo/colors. | Hosted checkout, receipt, and customer-facing pages show the intended recognizable business identity. | High |  |  |  |  | Not Started
L-05 | Staff | Create production staff account, verify login, then remove bootstrap password from runtime configuration. | Staff access works and bootstrap secret is removed. | Critical |  |  |  |  | Not Started
L-06 | First family | Create one controlled real family and athlete with a real email. | Registration, waiver, USA submission, and family scoping work. | Critical |  |  |  |  | Not Started
L-07 | Small live charge | Create a low-cost temporary live product and complete one real purchase. | Correct amount settles; order completes; package activates; receipt uses intended branding. | Critical |  |  |  |  | Not Started
L-08 | Live check-in | Verify USA card, then check in the controlled athlete. | Eligibility and attendance operate correctly in production. | Critical |  |  |  |  | Not Started
L-09 | Live refund | Refund the low-cost order in DenOS. | Money is refunded, order is Refunded / canceled, package is inactive, and audit trail remains. | Critical |  |  |  |  | Not Started
L-10 | Live subscription | Use a temporary low-cost installment product, confirm first access, then cancel/refund. | Subscription lifecycle, invoice webhooks, cancellation, and package eligibility work. | Critical |  |  |  |  | Not Started
L-11 | Backups | Run a production DB backup and restore it into a separate test database. | Restore completes and key record counts reconcile. | Critical |  |  |  |  | Not Started
L-12 | Monitoring | Force an API error and verify hosting alerts/log access. | Owner receives actionable notification without secrets or sensitive data. | High |  |  |  |  | Not Started
L-13 | Policies | Verify privacy, terms, refund/cancellation, and support contact links. | Parents can review policies before purchase and find support details afterward. | High |  |  |  |  | Not Started
L-14 | Password recovery | Complete a real password-reset email flow. | Single-use reset works and old credentials/tokens are handled safely. | Critical |  |  |  |  | Blocked
L-15 | Go-live approval | Review every Critical and High test with owner. | All Critical tests Pass; unresolved High tests have owner and resolution date. | Critical |  |  |  |  | Not Started

## Launch checklist
Launch checklist
Do not store actual secrets here. Record only the secret name and confirmation that it was configured.
ID | Workstream | Launch task | Owner | Target date | Dependency / secret | Completion evidence | Status
D-01 | Hosting | Deploy the React frontend to Vercel; select a container-capable host for the ASP.NET Core API. |  |  | Vercel plus API-host account and billing | Production service URLs | In Progress
D-02 | Database | Provision managed PostgreSQL production database. |  |  | ConnectionStrings__LegacyOS | Health check and migration log | Not Started
D-03 | Packaging | Add production Docker/build configuration and environment-based frontend API URL. |  |  | Hosting provider selected | Successful deployment build | Not Started
D-04 | Domain | Connect thedenfranklin.com (or the approved app subdomain) to Vercel and point api.thedenfranklin.com to the API host. |  |  | Domain registrar/DNS access | DNS and HTTPS validation | Not Started
D-05 | TLS | Enforce HTTPS and secure redirects. |  |  | Domain configured | Browser certificate check | Not Started
D-06 | CORS | Set exact production frontend origin. |  |  | Cors__AllowedOrigins__0 | Cross-origin test | Not Started
D-07 | Stripe | Configure Stripe live secret and webhook secret. |  |  | Stripe__SecretKey; Stripe__WebhookSecret | Successful live webhook | Not Started
D-08 | App URL | Set the production frontend and Stripe return URLs to the approved thedenfranklin.com HTTPS URL. |  |  | Frontend__BaseUrl | Checkout return test | Not Started
D-09 | Branding | Configure DenOS name, logo, icon, colors, receipts, and support details in Stripe. |  |  | Stripe Dashboard access | Live checkout screenshot | Not Started
D-10 | Backups | Enable automated DB backups and document restore procedure. |  |  | Managed DB plan | Successful restore test | Not Started
D-11 | Monitoring | Configure uptime/error monitoring and owner notifications. |  |  | Alert destination | Test alert | Not Started
D-12 | Email | Select transactional email provider and verified sending domain. |  |  | Provider API key and DNS | Delivered test email | Not Started
D-13 | Recovery | Implement password-reset request and single-use token flow. |  |  | Transactional email | Automated tests and live test | Blocked
D-14 | Legal | Publish privacy, terms, refund/cancellation, and contact pages. |  |  | Approved policy text | Public URLs | Not Started
D-15 | Data reset | Back up sandbox DB, then initialize a separate empty production DB. |  |  | Production DB | Record-count sign-off | Not Started
D-16 | Admin | Create named production staff users and remove bootstrap password. |  |  | BootstrapStaff credentials | Staff access sign-off | Not Started
D-17 | Products | Recreate approved production products, installment rules, and discounts. |  |  | Final price list | Staff review | Not Started
D-18 | Waiver | Upload approved production waiver and confirm required status. |  |  | Final signed-off PDF | Hash/version check | Not Started
D-19 | First members | Onboard first two controlled members and observe registration through check-in. |  |  | Member consent | Completed first-member sheet | Not Started
D-20 | Launch | Remove temporary live products and announce production enrollment URL. |  |  | All critical tests pass | Owner approval | Not Started

## First members
First members
Use consenting controlled members. Resolve issues before opening enrollment broadly.
Member | Stage | Action | Expected result | Completed by | Date | Evidence | Issue / follow-up | Status
Member 1 | Invite | Send private production enrollment URL. | Correct DenOS page opens over HTTPS. |  |  |  |  | Not Started
Member 1 | Register | Guardian creates account and athlete. | Family scope, valid email, USA number, and waiver are recorded. |  |  |  |  | Not Started
Member 1 | Verify | Staff verifies USA Wrestling membership. | Card is Current through August 31 and leaves review queue. |  |  |  |  | Not Started
Member 1 | Purchase | Guardian buys approved product. | Correct live price, branding, receipt, Completed order, and active package. |  |  |  |  | Not Started
Member 1 | Check-in | Staff completes first check-in. | Attendance appears and balance changes correctly. |  |  |  |  | Not Started
Member 1 | Support | Guardian signs out/in and reviews account. | Family, athlete, package, waiver, and order are correct. |  |  |  |  | Not Started
Member 2 | Invite | Send private production enrollment URL. | Correct DenOS page opens over HTTPS. |  |  |  |  | Not Started
Member 2 | Register | Guardian creates account and athlete. | Family scope, valid email, USA number, and waiver are recorded. |  |  |  |  | Not Started
Member 2 | Verify | Staff verifies USA Wrestling membership. | Card is Current through August 31 and leaves review queue. |  |  |  |  | Not Started
Member 2 | Purchase | Guardian buys approved product. | Correct live price, branding, receipt, Completed order, and active package. |  |  |  |  | Not Started
Member 2 | Check-in | Staff completes first check-in. | Attendance appears and balance changes correctly. |  |  |  |  | Not Started
Member 2 | Support | Guardian signs out/in and reviews account. | Family, athlete, package, waiver, and order are correct. |  |  |  |  | Not Started